AI ASSISTANT HEALTHCARE

Project Manager / Technical Handover

Fire TV-first Personal Health, Care & Wellness Companion

PURPOSE This document hands the project to another project manager or coding agent. It records the product intent, decisions, architecture, safety rules, work completed, current status, immediate next action, delivery plan and implementation rules. The goal is exact continuity, not a redesign.

| Item | Current value |
| --- | --- |
| Project | AI Assistant Healthcare |
| Primary platform | Amazon Fire TV / Fire TV Stick |
| Hackathon | Build, Ship, Shape: Amazon Developer Hackathon 2026 |
| Primary track | Fire TV |
| Handover date | 28 September 2026 |
| Submission deadline | 23 October 2026, 12:00 pm PT |
| Current gate | P1 local build passed; physical Fire TV validation pending |
| Client | Fire OS + Kotlin + Jetpack Compose for TV |
| Backend | Python/FastAPI + SQLite |

# 1. Executive Handover Summary

AI Assistant Healthcare is a Fire TV-first health, care and wellness companion. It is designed to help a person follow information they already received from healthcare professionals and help a healthy/time-constrained user complete bounded wellness activity. Fire TV is the hero product.

| Regime | Purpose | AI role | Hard boundary |
| --- | --- | --- | --- |
| ASSIST / Care | Organize doctor-provided information into a dated, source-attributed routine. | Transformer only. | No diagnosis, prescription, dose change or invented clinical content. |
| GUIDE / Wellness | Create/sequence a routine for time, goal and preferences. | Generator inside safety envelope. | Uses curated movement catalog and deterministic validation. |

CORE LOOP Verified/user-provided information → AI organization/personalization → Today's actions → completion → Progress → Daily Summary → next-day plan.

## Non-negotiable continuity rules

Both Care and Wellness remain in the MVP; the project must not collapse into a fitness-only app.

Fire TV remains the primary experience; companion web/mobile is only for awkward tasks such as document upload.

Clinical information is never auto-confirmed. Human confirmation is required before it affects the care plan.

Every health value keeps source, date and context; historical values are never presented as live/current.

ASSIST is transform-only. GUIDE is catalog-constrained.

Care path must work offline after confirmation; safety failures fail closed.

Use synthetic/demo data; never put real patient documents in the repository.

Implementation is phase-gated. Do not add random features or change architecture without owner approval.

# 2. Source-of-Truth Documents

| Document | Purpose | How to use |
| --- | --- | --- |
| Project_Master_Spec.md | Authoritative WHAT/WHY: product, personas, journeys, UX, safety, privacy, scope. | Read before changing product behaviour. |
| PROJECT_REVIEW.md | Adversarial review of scope, conflicts, safety gaps, risks and demo spine. | Read to understand why key decisions exist. |
| ARCHITECTURE_MVP_PLAN.md | HOW: 30 architecture decisions, lock, phases, team split, DoD. | Treat D1–D30 as locked unless owner approves a change. |

IMPORTANT An older wellness-only draft existed in project history. It is not the current product definition. The current product is Care + Wellness.

# 3. Product Definition

## 3.1 Care / Health Companion

Representative situation: a person recovering from a serious cardiac/neurological event is stable at home and has medicines, prescribed exercises, meal instructions, precautions, tests and follow-ups spread across documents. The product begins after clinical decisions have already been made.

Extract relevant information from doctor-provided documents.

Create proposals with source/date/reference.

Human reviews the proposal against the original document.

Only confirmed items enter the care plan.

Today shows Now / Next / Done.

Medication instructions preserve the dose wording as transcribed.

Prescribed exercises remain clearly labelled as prescribed.

Meal instructions, precautions, appointments and tests can be shown.

Recorded measurements show value, unit, observation date, source and context.

Plain-language explanations only simplify the confirmed source; they do not add medical knowledge.

## 3.2 Wellness / Fitness Companion

Representative request: “I have 10–20 minutes before work. Give me a quick workout to kick-start my day.” The product uses time, goal, preferences and relevant context to create a bounded routine.

| Example 15-minute structure | Duration |
| --- | --- |
| Warm-up | 2 min |
| Mobility | 5 min |
| Light exercise | 5 min |
| Cooldown/breathing | 3 min |

## 3.3 Both user

Care and wellness remain distinguishable.

A prescribed exercise is clinical instruction; an AI wellness routine is not.

A wellness routine must never replace or merge with prescribed exercise.

Confirmed precautions must be surfaced before generated wellness activity.

# 4. Personas

| Persona | Role | Need |
| --- | --- | --- |
| Ramesh — Care | 62, retired, post-event, alone on weekdays. | Clear “what now”, source-backed instructions, completion record. |
| Priya — Wellness | 34, employed, time-constrained. | A sensible 10–20 minute routine with low decision overhead. |
| Anjali — Both | 48, has doctor-provided care routine plus fitness goals. | One day view without mixing care and wellness safety rules. |
| Meera — Caregiver | Supporting setup/confirmation role. | Trustworthy review/correction and readable progress. |
| Clinician | Out-of-band source of instructions; not an app user. | Product must faithfully show what was provided. |

# 5. Core User Journeys

## 5.1 Care setup

Launch → Profile Select → choose Care/Wellness/Both.

Optional care-team/contact information is user-entered only.

Add doctor-provided documents without TV typing.

Process documents into proposed medications, exercises, meals, precautions, appointments and measurements.

Every proposal is Needs Review and does not affect the plan.

Review against the original document; Confirm, Edit or Discard.

Unclear content becomes “Unclear — needs a person”; never guess.

Confirmed items populate Care Plan and Today.

## 5.2 Ordinary care day

Launch → Profile Select → Today.

Now card is the largest/most relevant item and includes instruction + source/date.

Select → Item Detail → Mark as taken / Not now / Why this?.

Why this? provides a meaning-preserving simplification of the source.

Completion is recorded and Today advances.

## 5.3 Wellness 15-minute journey

Launch → Profile Select → Today.

Choose 10/15/20 minutes and optionally a goal.

Routine preview shows every segment and an explicit total.

Start → guided session; current activity, duration/reps, short instructions, progress and next activity.

Automatic transitions; Pause and Back available; remote can be put down.

Completion updates Progress and consistency; partial sessions are recorded honestly.

## 5.4 Shared TV privacy

Always open to Profile Select; never auto-enter a health profile.

Before entry, show name/avatar only — no condition, medication or adherence state.

Optional D-pad PIN for care profiles.

Profile switching clears the previous health information from view.

Sensitive read-aloud is opt-in.

# 6. Information Architecture / TV UX

| Level | Surface | Purpose |
| --- | --- | --- |
| Launch | Profile Select | Choose user/context without exposing health data. |
| Home | Today | Now → Next → shortcuts → Done; convergence point. |
| Care | Care Plan | Medications, prescribed activity, meals, precautions, appointments. |
| Health | Health Info | Recorded measurements with value/unit/date/source/context. |
| Wellness | Wellness | Start session, specific request, preview, guided player. |
| Progress | Progress | Recent activity, consistency, Daily Summary. |
| Documents | Documents | Document list + Review & Confirm. |
| Settings | Settings | Profile, context, PIN, spoken-output preference, orientation replay, reset. |

## 6.1 Fire TV interaction rules

Primary interaction: D-pad Left/Right/Up/Down, Select, Back.

Fully usable without voice.

No pointer/hover-first design and no typing-first flow.

10-foot UI, large readable text, large targets.

Body text minimum: 14sp.

Keep UI inside the inner 90% safe zone; avoid outer 5%.

Focus must always be clearly visible and not depend on colour alone.

Back moves one predictable level toward Today; it must not abandon a session without confirmation.

Shallow hierarchy; Today is the convergence point.

# 7. Feature Inventory

## 7.1 ASSIST

| ID | Feature | Phase |
| --- | --- | --- |
| F-A01 | Document intake without TV typing | MVP |
| F-A02 | Information extraction with source references | MVP |
| F-A03 | Mandatory human review/confirmation | MVP |
| F-A04 | Medication instruction display | MVP |
| F-A05 | Prescribed exercise display | MVP |
| F-A06 | Meal instruction display | MVP |
| F-A07 | Precautions display/gating | MVP |
| F-A08 | Appointments/follow-ups | MVP |
| F-A09 | Health Info dashboard | MVP |
| F-A10 | Meaning-preserving plain-language explanation | MVP |
| F-A11 | Care task completion | MVP |
| F-A12 | Basic document change handling | MVP/basic |
| F-A13 | Care/emergency contact card | MVP |
| F-A14 | Caregiver review on TV | MVP |
| F-A15 | Remote caregiver companion | P2 |
| F-A16 | Manual measurement entry | P2 |
| F-A17 | Full multi-document timeline | P3 |

## 7.2 GUIDE

| ID | Feature | Phase |
| --- | --- | --- |
| F-G01 | Natural-language request | MVP |
| F-G02 | Equivalent non-voice path | MVP |
| F-G03 | Routine generation/selection | MVP |
| F-G04 | Routine preview | MVP |
| F-G05 | Guided session player | MVP |
| F-G06 | Pause/resume/exit | MVP |
| F-G07 | Breathing/relaxation | MVP |
| F-G08 | Stretching/mobility | MVP |
| F-G09 | Precaution-aware gating | MVP |
| F-G10 | Basic preference memory | MVP/basic |
| F-G11 | Illustrated guidance | P2 |
| F-G12 | Spoken coaching cues | P2 |
| F-G13 | Camera-based form feedback | P3 |

## 7.3 PROGRESS / AI / CROSS-CUTTING

Activity log; routine completion; streak/consistency; Daily Health & Wellness Summary; behavioural insights.

AI: intent understanding, document structuring, simplification, routine generation, personalization, summarization, bounded Q&A and guardrails.

Cross-cutting: profile select, Care/Wellness/Both, optional PIN, profile switching, accessibility baseline, offline resilience, demo-data labelling, Settings and in-app reminders.

# 8. Daily Health & Wellness Summary

This is an end-of-day user-facing summary, not a medical report.

| Region | Content | Rule |
| --- | --- | --- |
| 1. Recorded facts | Completed/skipped/not-marked items, sessions, appointments. | Timestamped application records. |
| 2. Historical information | Recorded health values. | Always show observation date and source; never present as current. |
| 3. User activity | Sessions, durations, actions. | State what the user actually did. |
| 4. AI interpretation | Short summary + next-day plan. | Visibly separated and labelled AI-generated. |

# 9. AI and Safety Model

|  | ASSIST | GUIDE |
| --- | --- | --- |
| AI role | Transformer | Generator within safety envelope |
| Source of truth | Document/confirmed data | Safety envelope + user constraints |
| Output | Proposal with provenance | Catalog IDs + durations |
| Main failure | Invented clinical content | Unsafe routine |

## 9.1 Absolute prohibitions

No diagnosis.

No prescription/treatment recommendation.

No medication dose changes or calculations.

No invented medical/doctor instructions.

No unsupported medical recommendations.

No replacing the doctor.

No unsupported recovery/improvement/deterioration claims.

No emergency medical decisions.

No clinical content generated from general medical knowledge in ASSIST.

No clinical content or prompt bodies in logs.

TRUST MECHANISM The product's strongest architectural claim is the mandatory human confirmation gate: the reviewer compares the AI proposal against a rendered image of the original document page with the source region highlighted. The reviewer is not asked to validate the model against its own transcription.

# 10. Architecture Lock — D1 to D30

| ID | Locked decision |
| --- | --- |
| D1 | Fire OS (Android); Vega post-hackathon. |
| D2 | Kotlin + Jetpack Compose for TV; RN TV only if explicit Day-2 reversal trigger is hit. |
| D3 | minSdk 29; targetSdk 34. |
| D4 | One narrow backend required. |
| D5 | Single Python/FastAPI + SQLite service; API + minimal companion page. |
| D6 | Two stores: device Room canonical for confirmed clinical data; server SQLite/blob for docs/renders/proposals. |
| D7 | Text-layer synthetic PDFs; no OCR in MVP. |
| D8 | Claude via Anthropic API behind internal LlmClient; provider terms must be verified. |
| D9 | Sync short AI operations; job + poll for extraction. |
| D10 | Pre-generate AI-derived text at confirmation; confirmed care path offline. |
| D11 | Strict JSON schema, server validation, max 2 retries, fail closed; deterministic verbatim-dose substring check. |
| D12 | ASSIST transform-only; output always a proposal requiring confirmation. |
| D13 | GUIDE emits catalog IDs + durations, not movement free text. |
| D14 | Mandatory server-side guardrail; client render-time provenance assertions. |
| D15 | Server text + bounding-box extraction; no OCR. |
| D16 | Server-render original page with highlighted source; TV displays image beside proposal. |
| D17 | Versioned human-authored movement catalog bundled in backend + TV. |
| D18 | Deterministic device-side Day/Plan engine; no AI. |
| D19 | Deterministic device-side coroutine Session Runtime; no AI/network. |
| D20 | Three offline tiers: Tier 0 always works; Tier 1 degrades; Tier 2 needs network. |
| D21 | Minimal companion web page for upload/awkward text entry only; never health display. |
| D22 | Short TV pairing code; companion posts to backend; TV polls. |
| D23 | Small REST/JSON HTTPS API under /v1. |
| D24 | Every AI operation has named deterministic fallback; no silent failure. |
| D25 | Credentials server-side via environment variables; no client secrets. |
| D26 | Identifiers-only structured logs; clinical/prompt content not logged. |
| D27 | Two synthetic profiles + 6–7 synthetic docs; labelled as demo data. |
| D28 | One managed HTTPS backend; sideloaded APK; no Appstore submission. |
| D29 | Safety-weighted tests + manual TV checklist. |
| D30 | Resolve real target early; physical Fire TV preferred; target is a blocking gate. |

# 11. Key Technical Flows

## 11.1 ASSIST

Document → text + bbox extraction → transform-only AI → strict schema validation
→ safety guardrail → proposal + provenance + rendered original-page evidence
→ human Review & Confirm → device-canonical confirmed item
→ pre-generated plain-language text → deterministic Day/Plan → Today
→ completion → Progress → Daily Summary

## 11.2 GUIDE

Time / goal / preferences → GUIDE AI selects catalog IDs + durations
→ deterministic catalog/precaution/structure/duration validation
→ routine preview → deterministic Session Runtime → completion → Progress

## 11.3 Offline tiers

| Tier | Network | Contents |
| --- | --- | --- |
| 0 | Never required | Profile, Today, care plan, health info, completion, progress, session runtime, summary regions 1–3, preset routines. |
| 1 | Optional | AI routine generation → vetted preset; AI summary region 4 may be omitted. |
| 2 | Required | Document ingestion, extraction and confirmation-time pre-generation; UI must say so honestly. |

# 12. Companion Interface

Minimal mobile web page served by backend.

Only upload documents and handle awkward text entry/setup tasks.

Never display health information in companion.

Pair using a short code shown on TV.

TV polls for new documents.

Fire TV remains the primary product.

# 13. Work Completed and Current State

| Work | Status | Details |
| --- | --- | --- |
| Product concept | DONE | Care + Wellness defined as one product. |
| Current Master Spec | DONE / working source | Corrected spec is current product reference. |
| Project Review | DONE | Scope, conflicts, safety and demo risks reviewed. |
| Architecture MVP Plan | DONE | 30 decisions + lock + phases + team split + DoD. |
| Hackathon alignment | DONE | Fire TV track and submission requirements reviewed. |
| Local environment | DONE | JDK 17, Android SDK 34, Build Tools 34.0.0, ADB, Android Studio. |
| P1 build | PASSED LOCALLY | APK built and verified with aapt2. |
| Physical Fire TV test | PENDING | APK has been sent to teammate. |
| P2 | NOT STARTED | Wait for physical P1 validation. |
| Healthcare features | NOT STARTED | Begin only after P1/P2 gates. |

## 13.1 Exact P1 result

| Check | Result |
| --- | --- |
| Kotlin | 2.0.21 |
| Compose for TV | Used |
| Gradle | 8.9 |
| AGP | 8.7.0 |
| JDK | OpenJDK 17.0.20.1 LTS (Microsoft Build) |
| minSdk | 29 |
| targetSdk | 34 |
| compileSdk | 35 (build-time; target remains 34) |
| SDK platform | 34 |
| Build Tools | 34.0.0 |
| ADB | 1.0.41 / platform-tools 37.0.1 |
| APK | Generated and verified with aapt2 dump badging |
| APK path | C:\Users\Harshada Parab\Desktop\AI-Assistant-Healthcare\firetv\app\build\outputs\apk\debug\app-debug.apk |

CURRENT GATE P1 is passed on the development machine. The complete P1 gate remains open until the teammate confirms install + launch on the physical Fire TV Stick.

# 14. Immediate Next Step — P2

P2 is only the Fire TV interaction/focus proof. It is not the healthcare product.

One validation screen with at least six focusable cards.

Horizontal and vertical D-pad movement.

Every card reachable by D-pad.

Focus visible through scale + border + background change, not colour alone.

Focus retained after state changes.

Toggleable 5% safe-zone overlay.

14sp text sample + intended primary card size.

Test Select and Back.

Validate on the teammate's physical Fire TV.

Measure P1+P2 effort against the predefined D2 reversal trigger.

## P2 stop condition

After P2, stop and report pass/fail, target used, time taken, friction and whether the D2 reversal trigger was hit. Do not start product screens until the owner approves.

# 15. 26-Day Delivery Plan

| Day | Main work | Gate |
| --- | --- | --- |
| 1 — 27 Sep | Environment + P1; repo hygiene; synthetic docs begin. | P1 block. |
| 2 — 28 Sep | P2 focus/safe-zone; P4 document POC; API contract draft. | D2 reversal decision. |
| 3 — 29 Sep | P3 timed session; P4 complete; API contract freeze; P5 begins. | Contract frozen. |
| 4 — 30 Sep | P5 safety/schema/dose check; profile/back shell. | Phase 0 review. |
| 5–8 | Foundation, document pipeline, evidence image, proposals. | Day 8 proposals reach TV. |
| 9–13 | Review/Confirm, Room/provenance, Day/Plan, Today care flow. | Day 13 confirm → device → Today. |
| 14–16 | Movement catalog, GUIDE generation/validation, preview/session. | Day 16 routine reaches TV. |
| 17–19 | Completion, consistency, Daily Summary. | Day 19 summary integrated. |
| 20–22 | Companion, pairing, deployment, privacy/security/offline polish, provider-term verification. | Submission-critical integration. |
| 23 — 19 Oct | Full manual TV checklist; both journeys without voice/typing. | All TV checks pass. |
| 24 — 20 Oct | Offline rehearsal, degraded paths, <3 min demo, finalize script. | Demo ready. |
| 25 — 21 Oct | Record/cut video, description, Product Feedback, friction log, recheck HACK items. | Submission assets ready. |
| 26 — 22 Oct | README, repo access, secret scan, final regression, buffer. | Submit by 23 Oct 12:00 pm PT. |

# 16. Team Split

| Owner | Responsibilities |
| --- | --- |
| Developer A / Fire TV | Compose/Kotlin UI, design system, navigation/focus/Back, Room/provenance, Day/Plan, Session Runtime, all TV screens, Review & Confirm, offline behaviour, manual TV checklist. Owns P1/P2/P3. |
| Developer B / Backend + AI | FastAPI, PDF extraction/bbox, page render/highlight, ASSIST/GUIDE, LlmClient, guardrails, catalog, synthetic docs, companion/pairing, deployment, validator tests. Owns P4/P5. |
| Shared | API_CONTRACT.md, demo script, friction log, Product Feedback, README, integration sessions, final rehearsal/recording. |

## 16.1 Do not parallelize

Catalog before GUIDE AI.

API contract before client data layer.

Guardrail before AI surface ships.

P4 evidence pipeline before Review screen.

P1 before everything.

## 16.2 Safe parallelization

Design system ↔ document pipeline.

Day engine ↔ extraction.

Today screen ↔ guardrail.

Session runtime ↔ summary generator.

Catalog authoring ↔ client work.

Synthetic docs ↔ other work.

# 17. Definition of Done

| Area | Done when |
| --- | --- |
| Architecture | D1–D30 locked/deferred; API contract frozen; repo hygiene + judge access. |
| Fire TV | D-pad everywhere; visible/retained focus; safe zone; ≥14sp body text; predictable Back; provenance enforced in data layer. |
| ASSIST | Document → extraction → proposal/source → original-document confirmation → confirmed device instruction → Today → completion; source/date shown; dose mechanically checked. |
| GUIDE | Request → catalog generation → deterministic validation → preview → hands-free session → completion; precautions before session; preset fallback. |
| PROGRESS | Completions visible; streak accurate; partial sessions honest; four-region Daily Summary. |
| AI | Two regimes separate; guardrail mandatory/fail-closed; strict schemas + bounded retry; fallbacks rehearsed; no clinical content in AI logs. |
| Companion | Pair → upload → document appears on TV; companion shows no health information. |
| Submission | Repo, instructions, video <3 min, description, Product Feedback, friction log, final HACK check, deadline met. |

# 18. Key Risks

| Risk | Response |
| --- | --- |
| No runnable Fire TV target | Physical Fire TV is with teammate; P1 build done; physical launch is immediate gate. |
| Framework drift | Kotlin/Compose locked; RN only under explicit D2 trigger. |
| Scope inflation | Demo spine + gates; optional work never outranks gates. |
| Unsafe AI | Catalog + strict schema + guardrail + fail-closed tests. |
| Clinical hallucination | ASSIST transform-only + provenance + original-document confirmation. |
| Model validates its own transcription | Use rendered original page with highlighted source. |
| PHI in logs | Identifiers only; no clinical/prompt bodies. |
| Secrets | Server env only; no client keys; final secret scan. |
| Network failure | Care path Tier 0 offline; named fallbacks; offline rehearsal. |
| Shared-room privacy | Profile Select, optional PIN, no sensitive pre-entry, opt-in sensitive speech. |
| Provider terms | Verify before submission; use synthetic data regardless. |
| Demo length/story | Storyboard first; Day 24 timed rehearsal; cut before recording. |

# 19. Intended Demo Spine

| Beat | Time | Story |
| --- | --- | --- |
| 1 | 0:00–0:20 | Fire TV launch + Profile Select; introduce care problem. |
| 2 | 0:20–0:35 | Care profile → Today Now card with source/date. |
| 3 | 0:35–0:50 | Mark as taken → Today advances. |
| 4 | 0:50–1:35 | Documents → original page + highlight → Confirm → item reaches Today. |
| 5 | 1:35–1:45 | Out-of-scope clinical request declined/redirected. |
| 6 | 1:45–2:05 | Wellness → 15 min → goal → routine preview. |
| 7 | 2:05–2:30 | Hands-free guided session → completion/progress. |
| 8 | Remaining | Daily Summary + next-day plan. |

DEMO SAFETY No real patient data; no unsupported medical-improvement claim; no undated health value; no credential on screen; no voice dependency; rehearse offline; use silence/original audio unless rights are secured.

# 20. Hackathon Requirements Snapshot

Primary track: Fire TV. The project must launch a demo-ready app on Fire OS or Vega OS.

Any framework is acceptable if it runs on the target platform; current project uses Kotlin/Compose.

Repository must contain source code, assets and setup/run instructions.

Public repository needs an appropriate open-source license; private repository must be shared with required reviewers/testing access.

Demo video must show the project functioning on the intended platform.

Product Feedback is required for each developer tool/API/SDK used: what/why, what worked, what needs work, onboarding from zero to Hello World to working app, and Yes/No on using it again with why.

Submission materials must be in English or include English translation.

Third-party SDK/API/data use must comply with terms/licensing.

Avoid copyrighted music/material unless permission exists.

Official deadline: 23 October 2026, 12:00 pm PDT.

Friction logs can provide up to 10% judging bonus under the rules.

# 21. Claude / Coding-Agent Operating Rules

Read Project_Master_Spec.md, PROJECT_REVIEW.md and ARCHITECTURE_MVP_PLAN.md before changing code.

State phase objective, affected files, dependencies, risks and implementation plan before work.

Implement only the approved phase.

Do not silently change D1–D30.

Do not change the Master Spec/Review/Architecture Plan without owner approval.

Do not add random libraries, providers, screens or infrastructure.

Stop at every gate and report exact pass/fail results.

Keep clinical provenance and human confirmation mandatory.

Keep GUIDE catalog-constrained and deterministic validation mandatory.

Keep confirmed care path offline.

Never log clinical content or AI prompt/response bodies.

Never put API keys/secrets in client code, repo, build artifacts or demo assets.

Use synthetic demo data.

Every AI operation must have a named deterministic fallback; safety failures fail closed.

If something is unclear, ask the owner instead of redesigning the product.

# 22. Immediate Handover Checklist

| Step | Owner | Status |
| --- | --- | --- |
| P1 APK built | Current developer | DONE |
| APK shared with teammate | Current developer | DONE |
| Install APK on physical Fire TV | Teammate | NEXT |
| Confirm install + launch + screen | Teammate | PENDING |
| Approve P1 full gate | Owner | After device validation |
| Start P2 | Fire TV developer + Claude | After P1 |
| Test P2 on physical TV | Teammate | After P2 build |
| Check D2 reversal trigger | Owner | End of Day 2 |
| Continue next phase | Both | Only after gate approval |

# 23. Known Facts vs Pending Decisions

| State | Item |
| --- | --- |
| LOCKED | Fire OS / Android target. |
| LOCKED | Kotlin + Jetpack Compose for TV. |
| LOCKED | minSdk 29 / targetSdk 34. |
| LOCKED | FastAPI + SQLite backend. |
| LOCKED | ASSIST transform-only + human confirmation. |
| LOCKED | GUIDE curated movement catalog. |
| LOCKED | Original-document evidence rendered server-side. |
| CURRENT | P1 APK builds successfully. |
| PENDING | Physical Fire TV install/launch confirmation. |
| PENDING | P2 focus/safe-zone validation. |
| CONDITIONAL | RN TV only if D2 reversal trigger is hit. |
| VERIFY BEFORE SUBMISSION | AI provider terms and third-party licenses. |
| VERIFY BEFORE SUBMISSION | Final hackathon requirements, repo access, video, Product Feedback, friction log. |

# 24. Final Handover Statement

The project is intentionally at an early but controlled implementation point. Product definition, adversarial review, architecture and the first build gate are complete. The current responsibility is not to redesign the idea. It is to validate P1 on the teammate's physical Fire TV, complete P2, and then execute the approved plan through Care + Wellness end to end.

If a new project manager takes over, the correct mental model is: preserve the product intent, preserve the safety architecture, preserve the phase gates, and prioritize a real end-to-end demo spine over optional breadth.

# Appendix A — Source Materials

Current corrected Project Master Spec (authoritative product specification).

PROJECT_REVIEW.md (adversarial review and risks).

ARCHITECTURE_MVP_PLAN.md (30 decisions, lock, execution plan, team split and DoD).

Project execution updates through 28 September 2026 (environment + P1 build + device handoff).

Official Amazon Developer Hackathon 2026 rules/resources checked for current Fire TV requirements.